| - Extra-ordinary Committee Meeting – 2022 (No. 113) |  |
| --- | --- |
| Date: | - Tuesday 22nd February, 2022 |
| Time: | - 08:00 – 09:00 GMT |
| Location: | - Online via Microsoft Teams |

- Discussion items

The meeting objective was to discuss further the conference planning for 2022 (Belfast), considering the instabilities and uncertainties associated with the continued COVID pandemic.

FM circulated a conference update and the agenda.

Conference update

138 delegates are now registered with a further 12 ‘essential’ delegates to register (which includes 4 workshop coordinators and the two plenary speakers – other are sponsors).

| Registration Type |  |
| --- | --- |
| Registration Type | CountOfID |
| Complimentary Registration | 11 |
| Early Bird - Member In-Person | 55 |
| Early Bird - Non Member In-Person | 25 |
| Early Bird - Student In-Person | 32 |
| Remote | 12 |
| TOTAL | 135 |

32 registered for the Young scientist event which QUB are organising and paying for directly.

About 60 registered for a poster submission.

Assuming minimal menu choices, currently sitting about £4,000 loss.  Sponsorship about £23,000.

We would need about 10 more not to incur a loss, which we will probably have. We are therefore expecting to make a small loss or even break even.

Agenda Items / queries

- Video recording contingency.

We will inform their speakers that this will be the contingency measure, so they should be prepared to send us a video IF they are not able to travel last minute, and a co-author is not able to present for them.  We will NOT require that everyone record a video, it is their choice whether they want to record one anyways as a safety measure, or record one only if it is confirmed that they cannot come.

We should draft an email together to send to all. It will them be sent out to all speakers by PR, the same way they all got information about the presentations in the last weeks. This is to be done 2 weeks before the conference.

FM will reach out to the keynote speakers already now.

The files would be too big for emails. FM will communicate with the PCO about how to setup that the speakers send them the videos.

(a) FM to talk to the PCO about setting up a way for speakers to transfer them the files

(a) MM will draft an email and circulate. PR to send to all speakers 2 weeks before the conference.

(a) FM to reach out to the keynote speakers about this contingency.

- Proceedings –electronic & hard copy access.

PR working on it. MM offered help. We are on time.

How many hard copies do we need? NONE. There was no option during the registration to ask for a hard copy, those who want one will have to order themselves from the printer (Amazon).

Do we need to adjust the template? The main issue that doesn’t work is the 60pt space at the beginning (new Word formats don’t allow it and we haven’t found a work around for it). To be discussed in another meeting.

- Tuesday committee meeting 2-5?

We will try to start at 13:00h, as most of us will probably fly in the day before. A light lunch will be available at the start, and the room will be available until 18h if we need. This is at the conference venue.

We should have a list with each other’s phone number.

(a) Everyone to email FD their phone number. FD will email the full list back to everyone.

- Tuesday evening meal – 2 course – invite plenary & Damien Barrett.  Time?

YES, invite Damien Barrett and the plenary speakers.

It should be planned for 19:00h.

- Burden of disease satellite meeting Tuesday.  North coast walk Saturday (Simon More?)

No action required from us, just to inform the committee.

EF informs that the KLM Saturday flight to Amsterdam is cancelled, so people will be interested in a Saturday activity.

- FM will contact Hannah and Simon about the walk.

- AOB.

Post-conference meeting – planned for Friday after lunch, at the venue, directly after lunch (which will be a take-away lunch available to delegates).  We start as soon as possible after lunch (probably around 13:30h, and try to keep it short).

Nominations for the committee – so far only one nomination (we have 2 positions up, and hope to keep LC). The committee may forward the call for nominations to people they think would be good additions.

(a) FD to send a last reminder to the membership. Should also remind people to register for the conference (confirm that will have an in-person meeting).

The next extraordinary meeting (March 8th, 16:00 CET) is likely not to be needed. It will be kept in our calendars in case needed, but FM will reach out to members individually if actions/help are needed.