| - Extra-ordinary Committee Meeting – 2022 (No. 112) |  |
| --- | --- |
| Date: | - Thursday 27th January, 2022 |
| Time: | - 11:30h – 12:30h GMT |
| Location: | - Online via Microsoft Teams |

- Discussion items

The meeting objective was to discuss further the conference planning for 2022 (Belfast), considering the instabilities and uncertainties associated with the continued COVID pandemic.

FM circulated the agenda.

Agenda Items / queries

- Postponement of early bird registration to 21 February (3 weeks later).

65 delegates are now registered with a further 37 ‘essential’ delegates to register (which includes 11 speakers).

| Registration Type |  |
| --- | --- |
| Registration Type | CountOfID |
| Complimentary Registration | 1 |
| Early Bird - Member In-Person | 35 |
| Early Bird - Non Member In-Person | 9 |
| Early Bird - Student In-Person | 14 |
| Remote | 6 |

Links for free registrations have now been issued to bursary and workshop coordinators to enable them to register.

The committee accepted the suggested postponement of the early bird registration by 3 weeks, with a new deadline of 21st February. DB in his position as the treasurer advised that it will be better to increase our number of registered, than to ensure that those registering later ay full price.

COVID policy on the website? Or leave it up to individuals (the conference organization worries only with legal requirements and individuals are to take their own risk assessments)?

Considering the differences between countries – it would be good to inform non British delegates what are the requirements and current recommendations in the UK (what to expect when entering Northern Ireland, as well as the requirements to attend dinner, enter the social venues, etc). Because the situation is so dynamic, however, it would not be wise to write out any recommendations on the website, but rather just add a link to the information directly from the competent authorities in Northern Ireland. GS suggests that we also send that link to all the delegates via email.

(a) Extend the early-bird registration deadline on the website

(a) For the LCO to make sure that on the website/programme there is information about the type of venue for each event, and a link to the relevant authority website

(a) for the secretary to send the same information by email to the membership as well as non-members already registered.

- Poster submissions acceptable from online delegates.

The committee unanimously agreed that this is not desirable, as part of the evaluation of the poster has to do with the author’s ability to communicate their research.

- Contingency – can switch to online at a later date.

Individual speakers may not be able to come in person despite plans (last minute sickness/positive). FM will have to check with the LCO whether we would be able to accommodate either a speaker presenting online, and/or pre-recording their presentation.

The committee discussed even the possibility of asking every presenter to pre-record their presentation as a contingency measure in case they are sick at the time of the presentation. This idea was ultimately discarded and some suggested that it is better to avoid any alternatives to coming in person. But we emphasized that the LCO should check the option to present online.

(a) For FM to discuss with the LCO the contingency plan in case oral presenters can’t come in person to the conference due to last minute illness/positive COVID test.

A contingency plan for an even worse case scenario will have to be discussed if it comes to that. We are not sure whether the LCO would run the online conference in that case, or we would have to take over and do it like we did in 2020. It was decided to leave another extraordinary committee meeting scheduled for 2 weeks before the meeting, in case we need to discuss an emergency plan then.

- Query regarding delegate – speaker was an MSc student when abstract submitted.

This seems to be a recurring issue and we need to have a decision about what to do in case students submit abstracts, but are no longer students at the time of the conference.

The committee votes for a yes in this case to the student rate, but GS suggests that we discuss this again in an ordinary committee meeting and make it a policy. The suggestion is that a general rule, however, for the future it is the status at the time of registration that counts.

(a) FD to add the item to the next Fall meeting

- Poster and SRUC prize amounts & certificates

Certificate templates are in the membership internal area. TV will send the ones he has to FM.

- AOB

Next extraordinary meetings to discuss potential COVID issues:

February 22nd (1 month before the conference): 9:00 CET.

March 8th : 16:00 CET

GS will send out Teams links