| # 2020 Extraordinary Committee Meeting Minutes (No. 106) |  |
| --- | --- |
| Date: | # Thursday 22 October 2020 |
| Time: | # 10:00h – 11.00h UK time |
| Location: | # Online via Microsoft Teams |

- Apologies for absence – none

- Format of SVEPM 2021 conference

- A decision was made unanimously to cancel the in-person conference in Toulouse and convert to online because of the ongoing uncertainty created by the Covid-19 situation.

- The conference will be held over 2 days – Thursday 25 March and Friday 26 March.

- Update on SVEPM 2021 plans

- Cancellation fees – the venue were going to charge 30% of the fee (€ 5000) for cancelling the in-person conference, but following negotiations form the PCO, this has been reduced to about 15% (€ 2340) if we use the same venue again in 2024. The venue currently hold the € 4000 which we paid to them in the summer, and propose to keep it as a deposit for 2024.

- Registration fees for SVEPM 2021

- Discussion around what the registration fees should be if fully online, given the need to make it financially attractive and having a significant differentiation between early and late registration, and member and non-member.

- The following fees (option 2) were agreed upon after looking at three costing options:

| Category | Early bird | Late |
| --- | --- | --- |
| Member students | € 150 | € 200 |
| Members and non-member students | € 200 | € 250 |
| Non-members | € 250 | € 300 |

- Presentations at SVEPM 2021 online

- The presentations should all be delivered live, despite the extra cost for the conference technology.

- Questions will be fielded after the live presentation, as usual.

- Video-conferencing ‘side-rooms’ could be used for the presenter to meet with attendees for further discussions.

- New programme needs to be drafted. ACTION: Draft new programme (GvS, TV).

- Cost of online conference platform

- The PCO can provide the online conference software in a newly developed technology.

- The cost of this platform is quite expensive, making it difficult to generate a profit for the conference at the fees agreed above.

ACTION: Approach PCO to ask for a more competitive price for hosting the conference – compare to Teams as a free alternative (TV).

- Conference workshops

- Workshops can be offered on the day before the conference begins in an online format using the same conference platform.

- Martin Green’s group cannot offer their workshop in an online format – that only leaves 4 viable workshops.

ACTION: Approach Alexis Delabouglise (CIRAD) and one of the local sponsoring companies who have both offered a workshop and ask to fill in proposal forms for committee circulation and approval (TV).

- Conference advertising

- Ask the PCO to update the conference website. ACTION: TV

- Advertise widely on social media – Twitter, EpiVet, Linkedin. ACTION: TV

- Contact the membership and oral presenters as soon as the programme is ready. ACTION: PR, GvS

- Next meeting

- Thursday 12th November 2020, 10.00am – 11.30am UK time.

Philip Robinson

SVEPM Honorary Secretary